# [Insert document name]

Subtitle (if needed)

Contents

1. Project Overview	3

2. Project Phases (Hybrid Agile–SDLC)	4

Phase 1 – Initiation & Requirements (SDLC)	5

Phase 2 – Analysis (SDLC + Agile Backlog Creation)	5

Phase 3 – Design (SDLC)	5

Phase 4 – Iterative Development (Agile Sprints)	5

Phase 5 – Testing (Agile + SDLC)	6

Phase 6 – Deployment (SDLC)	6

Phase 7 – Training & Documentation	6

Phase 8 – Post‑Implementation Review	6

3. Task Types	7

SDLC Task Types	7

Agile Task Types	7

4. Inputs, Outputs & Control Structures (Per SDLC Stage)	7

Initiation	7

Analysis	7

Design	8

Development (Agile Sprints)	8

Testing	8

Deployment	8

Post‑Implementation Review	8

5. Resources Required	8

Human Resources	9

Technical Resources	9

Documentation Resources	9

6. Project Schedule (Gantt Chart)	10

PROJECT PLAN

# 1. Project Overview

The Sports Warehouse Online Shopping Portal project will deliver a scalable, secure, and fully functional e‑commerce system within six months, as required by the business case. The business case states: “The system will be developed and implemented in six months from today.”

The project will follow a Hybrid Agile–SDLC methodology, combining structured SDLC governance with Agile iterative development and a prototype delivered at the 3‑month mark. The business case confirms: “A prototype approach will be followed… available for testing three months from the start date.”

# 2. Project Phases (Hybrid Agile–SDLC)

### Phase 1 – Initiation & Requirements (SDLC)

- Confirm business requirements

- Stakeholder interviews

- Requirements specification

- Risk identification

- Constraints and assumptions validation

- Approval to proceed

### Phase 2 – Analysis (SDLC + Agile Backlog Creation)

- Functional and non‑functional requirements

- User stories and acceptance criteria

- Prioritised product backlog

- Technical feasibility review

### Phase 3 – Design (SDLC)

- System architecture

- Database schema

- UI/UX wireframes

- Security design

- Hosting and infrastructure design

- Prototype design

### Phase 4 – Iterative Development (Agile Sprints)

- 2–3 week sprints

- Sprint planning, daily stand‑ups, sprint reviews

- Incremental development of:

  - Product catalogue

  - Customer access

  - Shopping cart

  - eCommerce

  - Reporting

- Prototype delivered at end of Sprint 4 (Month 3)

### Phase 5 – Testing (Agile + SDLC)

- Continuous testing during sprints

- Formal system testing

- Integration testing

- Performance testing (must support 2,000 → 60,000+ transactions/week) The business case states: “Initially supporting at least 2000 transactions a week but able to scale up to supporting an excess of 60,000 transactions per week.”

- User Acceptance Testing (UAT)

### Phase 6 – Deployment (SDLC)

- Deployment to production

- Data migration

- Security validation

- Go‑live

### Phase 7 – Training & Documentation

- User training

- Administrator training

- Technical documentation

- User guides

### Phase 8 – Post‑Implementation Review

- Lessons learned

- Benefits realisation

- Final report

# 3. Task Types

### SDLC Task Types

- Requirements gathering

- Analysis

- Design

- Testing

- Deployment

- Documentation

### Agile Task Types

- User stories

- Sprint tasks

- Bug fixes

- Enhancements

- Backlog refinement

- Sprint reviews

# 4. Inputs, Outputs & Control Structures (Per SDLC Stage)

### Initiation

- Inputs: Business case, constraints, budget

- Outputs: Project charter, stakeholder register

- Controls: Approval gates, risk register creation

### Analysis

- Inputs: Stakeholder interviews, business requirements

- Outputs: Requirements specification, user stories

- Controls: Requirements sign‑off, backlog prioritisation

### Design

- Inputs: Requirements, user stories

- Outputs: Architecture diagrams, UI wireframes, database schema

- Controls: Design review meetings, security review

### Development (Agile Sprints)

- Inputs: Prioritised backlog

- Outputs: Incremental working software, prototype

- Controls: Daily stand‑ups, sprint reviews, code reviews, GitHub version control

### Testing

- Inputs: Completed sprint increments

- Outputs: Test reports, defect logs

- Controls: Test plans, acceptance criteria, UAT sign‑off

### Deployment

- Inputs: Tested system

- Outputs: Live system, deployment report

- Controls: Deployment checklist, rollback plan

### Post‑Implementation Review

- Inputs: Project outcomes, performance data

- Outputs: PIR report, lessons learned

- Controls: Governance review

# 5. Resources Required

### Human Resources

- Project Manager

- 3 Developers

- UI Designer

- Business Analyst

- 2 Testers

- 2 Stakeholders The business case confirms: “A team of 10 people in total has been established for this project.”

### Technical Resources

- GitHub (source control)

- Microsoft Project (scheduling)

- Trello (Agile sprint management)

- Microsoft Teams (collaboration)

- Development workstations

- Servers (primary + secondary site) The business case states hosting must be internal with a secondary site.

### Documentation Resources

- Requirements specification

- Design documents

- Test plans

- Risk register

- Communication plan

- Quality management plan

# 6. Project Schedule (Gantt Chart)

## Updates

Due to server unavailability, team member sick leave, and the introduction of a banking integration requirement, the development start date has shifted from 30/03/2026 to 17/04/2026. A new 25‑day task has been added to accommodate the banking integration work. All subsequent development, testing, and deployment phases have been adjusted accordingly. Development will temporarily commence on developer workstations until servers arrive.

In accordance with the ICT Governance Policy, these changes will be reported to the ICT Governance Group, as the policy states: “All ICT changes must be submitted to the ICTGG prior to implementation” and “Risks to ICT systems must be considered, with appropriate mitigation strategies identified.”

Project Schedule Update 
 Due to unforeseen circumstances, several changes were required to the project schedule. Sports Warehouse advised that the project servers, including the development server, will be delayed by two weeks. Additionally, two key technical team members were unavailable due to illness, resulting in an additional four days of delay. A new requirement was also introduced: integration with external banking software, which adds 25 days of development effort.

To maintain progress, development will temporarily commence on developer workstations until the servers arrive. All affected tasks have been rescheduled, and a new task titled Banking Software Integration Development has been added to the Gantt chart. All subsequent phases have been shifted accordingly.

In line with the ICT Governance Policy, these changes have been documented, impacts assessed, and the updated schedule will be reported to the ICT Governance Group as required by policy guidelines stating that “all ICT changes must be submitted to the ICTGG prior to implementation” and that risks must be monitored and mitigated.