# Project assessment

## Criteria

### Unit code and name

ICTPRG530 | Manage projects using software management tools

### Qualification/Course code and name

ICT50220 | Diploma of Information Technology

## Student details

### Student number

881539898

### Student name

Michael Khalil

## Assessment declaration

Note: If you are an online student, you will be required to complete this declaration on the TAFE NSW online learning platform when you upload your assessment.

This assessment is my original work and has not been:

- plagiarised or copied from any source without providing due acknowledgement.

- written for me by any other person except where such collaboration has been authorised by the Teacher/Assessor concerned.

### Student signature and date

M.MAHER

20/3/2026

Version:	20220406

Date created:	31 March 2022

© 2022 TAFE NSW
RTO Provider Number 90003 | CRICOS Provider Code: 00591E

This assessment can be found in the: Learning Bank

The content in this document is copyright © TAFE NSW 2022 and should not be reproduced without the permission of TAFE NSW. Information contained in this document is correct at the time of printing: 5 July 2022. For current information please refer to our website or your Teacher/Assessor as appropriate.

## Assessment instructions

Table 1 — Assessment instructions

| Assessment details | Instructions |
| --- | --- |
| Assessment overview | The aim of this assessment is to assess your knowledge and performance required to use software management tools, to manage a systems development project from initiation to completion. |
| Assessment event number | 2 of 2 |
| Instructions for this assessment | This is a project-based assessment that assesses your knowledge and performance of the unit. This assessment is in three (3) parts: - PART 1: Determine an appropriate software development methodology as well as appropriate software management tools - PART 2: Use the software management tools - PART 3: Monitor the use of the software management tools And is supported by: - Assessment checklist - Assessment feedback - Supporting documents: - Sports Warehouse Business Case - Sports Warehouse Overview Note: This assessment may contain links to external resources. If a link does not work, copy and paste the URL directly into your browser. |
| Submission instructions | On completion of this assessment, you are required to submit it to your Teacher/Assessor for marking. Where possible, submission and upload of all required assessment files should be via the TAFE NSW online learning platform. It is important that you keep a copy of all electronic and hardcopy assessments submitted to TAFE and complete the assessment declaration when submitting the assessment. |
| What do I need to do to achieve a satisfactory result? | To achieve a satisfactory result for this assessment you must answer all the questions correctly. If a resit is required to achieve a satisfactory result it will be conducted at an agreed time after a suitable revision period. |
| What do I need to provide? | - TAFE NSW student account username and password. If you do not know your username and password, contact your campus or service centre on 131601. - Computer or other device with word processing software and internet access. - Writing materials, if required. - Access to fellow students for role-play situations. |
| What the Teacher/Assessor will provide | - Access to this assessment and learning resources, including the student workbook and any supporting documents or links: - ICTPRG530_AE_Pro2of2_Appx_SportsWarehousePortalFiles (Long URL: https://share.tafensw.edu.au/share/items/9ca215f3-9cb3-4c9b-b8cf-c074d5645502/0/?attachment.uuid=54c982ba-9d35-4b24-8769-1ab0e570fc2b) - Access to relevant software management tools. - Access to organisational policies and procedures. - Other supporting documents and raw files relevant to the assessment. |
| Due date Time allowed Delivery location | Refer to the training schedule 8 hours (indicative only) TAFE NSW campus/ TAFE Digital Campus/ TAFE NSW Moodle/ a location determined by your Teacher/Assessor Assessment is to be completed out of class |
| Assessment feedback, review or appeals | In accordance with the TAFE NSW policy Manage Assessment Appeals, all students have the right to appeal an assessment decision in relation to how the assessment was conducted and the outcome of the assessment. Appeals must be lodged within 14 working days of the formal notification of the result of the assessment. If you would like to request a review of your results or if you have any concerns about your results, contact your Teacher/Assessor or Head Teacher. If they are unavailable, contact the Student Administration Officer. Contact your Head Teacher/Assessor for the assessment appeals procedures at your college/campus. |

## Specific task instructions

The instructions and the criteria in the following tasks and activities will be used by the Teacher/Assessor to determine if the student has satisfactorily completed this assessment event. Use these instructions as a guide to ensure the student demonstrates the required knowledge and skills.

If this assessment requires the student to record information, the Teacher/Assessor will provide the appropriate document/template.

The student will record their participation and submit as video evidence. Alternatively, the Teacher/Assessor will advise a time and location for each event.

If the student is submitting video evidence, they must:

- provide a video for each participation clearly meeting all requirements

- ensure they have access to the equipment and resources required to participate in each demonstration

- follow the Video recording instructions (pdf). This one-pager includes useful tips, links to resources, and a demonstration video.
(Long URL: https://share.tafensw.edu.au/share/items/744af7d4-a241-45e2-adb0-0e13f2fe4950/0/?attachment.uuid=01c3c87a-4599-48c2-91f0-68a00b5bbb4c)

- address the items listed in the checklist, either during the demonstration or record them in a separate video file.

## Scenario

You work with Gelos Enterprises as a project manager in their Information and Communication Technology (ICT) Services department. You have been recently brought onto a project that Gelos is completing for a new client – Sports Warehouse.

Here’s a brief outline about the client.

Sports Warehouse is based in the Illawarra Region in NSW, Australia. The company is a reseller of athletic clothing, sports equipment and accessories sourced from local Australian manufacturers as well as big global brands. The leadership team at Sports Warehouse have established some strategic goals like increasing sales and creating brand awareness - they believe that implementing an online shopping portal is key to achieving their strategic goals.

Sports Warehouse has engaged Gelos Enterprises for assistance with developing and implementing the online shopping portal and have set a deadline of six months from today.

As a project manager you will be one of the key people involved in this project. Note that one of your colleagues has already prepared a business case for this project which includes key information like the proposed business solution, project risks, constraints, budget, and assumptions.

The business case has been approved by the leadership team at Sports Warehouse – you need to refer to it whilst managing the implementation and development of the shopping portal.

Here is a detailed overview about Sports Warehouse which includes their goals and objectives as well as their key requirements for the shopping portal. (Long URL: https://share.tafensw.edu.au/share/items/9ca215f3-9cb3-4c9b-b8cf-c074d5645502/0/?attachment.uuid=d8937253-2106-4db8-a5e9-ad7ce9bc91ad)

Here is a copy of the business case that your colleague prepared earlier. (Long URL: https://share.tafensw.edu.au/share/items/9ca215f3-9cb3-4c9b-b8cf-c074d5645502/0/?attachment.uuid=0ddde1e7-4989-4a3a-8125-e383820606b6)

## What do you need to do?

As a project manager on the Sports Warehouse engagement, you will be expected to:

- determine an appropriate software development methodology according to the system development project requirements

- determine appropriate software management tools for the project

- use the software management tools to document a project plan, define source-control procedures and create a collaborative environment for the project team

- monitor use of the software management tools to monitor and maintain the project plan, check accurate code entry and monitor the collaboration environment to resolve issues.

Essentially, you need to be across all aspects of the portal development to ensure it is completed effectively, and within the specified deadline.

Make sure you have read the Sports Warehouse overview and business case documents referred to earlier. Ideally, you should have both the documents open for reference as you work through this assessment.

Let’s get started!

## Part 1: Determine an appropriate software development methodology as well as appropriate software management tools

In this part of the assessment, you will need to:

- determine and recommend an appropriate software development methodology (Task 1)

- determine and recommend appropriate software management tools for the development and implementation of the online shopping portal (Tasks 2, 3, 4)

Consider the system development project requirements for the shopping portal before making your recommendations. Project requirements and associated information can be obtained from the Sports Warehouse overview and business case documents.

Task 1: Determine an appropriate software development methodology

In order to determine the required software development methodology according to the project requirements, ask yourself the following questions in order to arrive at a response – answers to some of these questions can be found in the Sports Warehouse overview and business case documents:

- What are the key project requirements for Sports Warehouse?

- What is the deadline for the project – can it be moved if needed?

- What is the budget for the project – is there a fixed or flexible budget?

- Are prototypes needed during the development?

Based on the answers to these questions, you should be able to determine an appropriate software development methodology - provide your recommendation and the reasons for doing so, in the space provided. Also outline the general processes and documentation that you will need to follow and create when using the chosen methodology. (Bullet points are fine, with a maximum of 250 words.)

### Recommended Methodology: Hybrid Agile–SDLC (Agile with SDLC governance) ### Reasons for Recommendation - Fixed, immovable deadline of six months requires structured planning and governance. The business case states: “The system will be developed and implemented in six months from today.” - Fixed budget of $150,000 requires controlled scope and formal documentation. The business case confirms: “The planned cost of the development is $150,000.” - Prototype required at 3 months, which aligns naturally with Agile iterations. The business case states: “A prototype approach will be followed… available for testing three months from the start date.” - High stakeholder involvement (CEO, IT Manager, Sales/Marketing, Operations) suits Agile’s iterative feedback cycles. - Strong governance requirements (weekly reporting, risk register, version control) require SDLC structure. The business case requires: “Weekly progress reporting… All risks must be recorded in the risk register.” - Scalability and security requirements benefit from SDLC’s formal design, documentation, and validation steps. ### General Processes to Follow - Initiation & Requirements (SDLC) - Requirements workshops, stakeholder interviews, business rules, constraints, risks, assumptions. - Iterative Development (Agile) - 2–3 week sprints, backlog refinement, sprint planning, daily stand‑ups, sprint reviews. - Design & Architecture (SDLC) - System architecture, database schema, security design, hosting design. - Prototype Delivery (Agile) - Early UI/UX prototype delivered at 3 months for stakeholder testing. - Testing (Agile + SDLC) - Continuous testing during sprints + formal system testing, UAT, performance testing. - Deployment & Review (SDLC) - Deployment plan, training, documentation, post‑implementation review.

Task 2: Determine an appropriate project management software

How will you go about choosing a project management software that aligns with the project requirements?

Ask yourself the following questions in order to arrive at a response – answers to some of these questions can be found in the Sports Warehouse overview and business case documents:

- What methodology will be followed for the software development project?

- What is the team size for the project?

- Would you like the project management software to track conversations and feedback to trigger actions?

- How will tasks be scheduled, tracked and assigned amongst the team members?

Based on the answers to these questions, you should be able to determine an appropriate project management software - provide your recommendation for the software, describe their general features and capabilities, and also provide reasons for your recommendation in the space provided. (Bullet points are fine, with a maximum of 250 words.)

### Recommended Project Management Software: Microsoft Project + Trello (Hybrid Use) ### Reasons for Recommendation - Supports the chosen Hybrid Agile–SDLC methodology - Microsoft Project provides structured scheduling, dependencies, critical path, and variance tracking—ideal for SDLC governance. - Trello supports Agile sprints, backlog management, and iterative task updates. - Team size of 10 requires clear task allocation and visibility The business case confirms: “A team of 10 people in total has been established for this project.” - Strict reporting and governance requirements The business case requires: “Weekly progress reporting via a project status / highlight report… All risks must be recorded in the risk register.” Microsoft Project supports baselines, variance tracking, and risk logs. - Fixed 6‑month deadline and fixed budget require precise scheduling and monitoring The business case states: “The system will be developed and implemented in six months… The planned cost of the development is $150,000.” - Prototype delivery at 3 months requires sprint‑based tracking Trello allows visual Kanban boards for sprint planning, daily stand‑ups, and rapid feedback cycles. ### General Features & Capabilities - Microsoft Project - Gantt charts, dependencies, resource allocation, cost tracking, baselines, variance reporting. - Ideal for managing fixed deadlines, critical path, and structured SDLC phases. - Trello - Kanban boards, checklists, labels, attachments, comments, activity logs. - Supports Agile ceremonies: sprint planning, backlog refinement, daily stand‑ups. ### How Tasks Will Be Managed - Microsoft Project: high‑level schedule, milestones, resource planning, risk tracking. - Trello: day‑to‑day task assignments, sprint boards, developer/tester workflow, feedback loops.

Task 3: Determine an appropriate source-control system

Now you need to determine an appropriate source-control system for the shopping portal project – how will you make an appropriate choice?

Ask yourself the following questions in order to arrive at a response – answers to some of these questions can be found in the Sports Warehouse overview and business case documents:

- What is the team size for the project?

- How many people will typically be involved in development at a given time?

Based on the answers to these questions, you should be able to recommend an appropriate source-control system - provide your recommendation for the system, describe their general features and capabilities, and also provide reasons for your recommendation in the space provided. (Bullet points are fine, with a maximum of 250 words.)

### Recommended Source‑Control System: GitHub ### Reasons for Recommendation - Team size of 10 requires a robust, multi‑user version control system The business case states: “A team of 10 people in total has been established for this project.” - Three developers will be working concurrently, meaning frequent code changes, branching, and merging must be handled cleanly. The business case lists: “3 developers” as part of the project team. - Agile–SDLC hybrid methodology requires continuous integration, iterative updates, and traceable version history, all of which GitHub supports. - High governance and reporting requirements demand a system with strong audit trails. The business case requires: “Weekly progress reporting… All risks must be recorded in the risk register.” GitHub’s commit history, pull requests, and issue tracking support this. - Supports distributed development, allowing developers to work from their own workstations—important because server delays are a known project risk. The business case notes: “Delay in delivery of network infrastructure (Servers) – risk potential medium.” ### General Features & Capabilities - Branching and merging - Feature branches, development branches, and protected main branch. - Pull requests with code review - Ensures quality control and prevents unapproved changes. - Commit history and version tracking - Full traceability of who changed what and when. - Issue tracking and project boards - Supports Agile sprints, backlog management, and bug tracking. - Integration with IDEs and CI/CD tools - Streamlines developer workflow and automated testing. ### Why GitHub Fits This Project - Handles multiple developers working simultaneously. - Supports structured SDLC documentation and Agile sprint workflows. - Provides secure, reliable, industry‑standard version control aligned with project governance needs.

Task 4: Determine an appropriate collaboration software

Lastly, how will you go about choosing an appropriate collaboration software for the shopping portal project - what sort of software will be useful for the project team to have discussions and share files?

Ask yourself the following questions in order to arrive at a response – answers to some of these questions can be found in the Sports Warehouse overview and business case documents:

- How often will the team need to communicate?

- What is the team size for the project?

- Does the project have multiple team members performing the same/similar tasks?

Note that Gelos is very particular about their internal and external communication being in line with organisational policies and procedures. Therefore, please ensure that you also refer to the following policies and procedures before recommending a collaboration software for the project.

- Digital Communications Policy and Procedure (Long URL: https://share.tafensw.edu.au/share/items/5f1cec7b-1d03-446a-85b7-edb42692c34e/0/?attachment.uuid=9a63a882-33e8-4b99-bb8d-95a66a12d6ca)

- Standard Operating Environment Policy (Long URL: https://share.tafensw.edu.au/share/items/5f1cec7b-1d03-446a-85b7-edb42692c34e/0/?attachment.uuid=6d3ef7dc-b21a-41f9-bb56-006f7e9551b4)

Based on the answers to the questions, as well as the guidelines in the organisational policies and procedures, you should be able to recommend an appropriate collaboration software - provide your recommendation for the software, describe their general features and capabilities, and also provide reasons for your recommendation in the space provided. (Bullet points are fine, with a maximum of 250 words.)

### Recommended Collaboration Software: Microsoft Teams ### Reasons for Recommendation - Team size of 10 requires a centralised communication platform The business case states: “A team of 10 people in total has been established for this project.” - Frequent communication is required due to weekly meetings, weekly progress reporting, and ongoing coordination between developers, testers, UI designer, BA, and stakeholders. The business case requires: “Weekly team meeting… Weekly progress reporting via a project status / highlight report.” - Multiple team members perform similar tasks (e.g., 3 developers, 2 testers), requiring shared channels, file sharing, and real‑time messaging. - Gelos policy mandates Microsoft Teams for online meetings Digital Communications Policy states: “Hold all online meetings using Microsoft Teams.” - Teams aligns with the Standard Operating Environment (SOE) The SOE lists Microsoft Office 365 as standard software, meaning Teams integrates seamlessly with Outlook, SharePoint, and OneDrive. - Supports secure, policy‑compliant communication Digital Communications Policy requires communications to be “professional… clear, concise, correct, and courteous” and prohibits sharing confidential or sensitive information via unapproved tools. Teams provides controlled access, secure channels, and organisational compliance. ### General Features & Capabilities - Chat & Instant Messaging - Real‑time communication, threaded conversations, status indicators. - Channels for each project area - Development, Testing, UI/UX, Requirements, Stakeholder Updates. - File Sharing & Versioning - Integrated with SharePoint/OneDrive for secure document storage. - Online Meetings & Video Calls - Required by Gelos policy; supports screen sharing and recording (with consent). - Task Integration - Planner/To‑Do integration for assigning and tracking work. ### Why Microsoft Teams Fits This Project - Fully compliant with Gelos policies. - Already part of the organisation’s approved software environment. - Supports structured, secure, and frequent collaboration for a 10‑person project team.

## Part 2: Use the software management tools

In this part of the assessment, you will need to demonstrate usage of the software management tools you identified in Part 1 of this assessment. This includes usage of the:

- project management software to document a project plan

- source-control system for defining the required source control procedures

- collaboration software to create a collaborative environment for the team.

Task 1: Document a project plan

Use the project management software determined in Part 1 along with other relevant software/tools as required (such as a word processing software), create a project plan addressing the following items.

The project plan must:

- use appropriate language and conventions

- use correct spelling and grammar

- use technical terminology

- be presented in a logical sequence

- use appropriate structure and layout.

The project plan must also include:

- The phases of the project, based on the software development methodology as well as the project risks:

  - Task types:

  - A clear description of the appropriate task types, according to the selected development methodology.

  - The inputs to and outputs from (control structures) each software development stage while executing each task type. These control structures must ensure the project complies with the selected methodology.

  - Any other resources needed that will support the development methodology.

- Schedule (Gantt chart) using the project management software identified earlier.

The project plan you just created will need to be submitted with this assessment – if you want, you can save the project plan as a PDF and submit that too.

Task 2: Define required source - control procedures

In this task you need to define the required source-control procedures, that is, what procedures would you expect your team to follow whilst using the source-control system identified earlier. These procedures should align with the software specifications and project requirements.

Remember that the Sports Warehouse overview and business case documents contain details about the project and software specifications.

The source-control procedures must include the:

- naming standards for version control and files

- folder structures/file organisation

- what determines a change of version?

- steps for entering and updating files.

Please outline a detailed procedure that addresses the bullet points above, for example, the procedure/rule around the naming standards for version control and files (bullet point 1) in the space provided. (Bullet points are fine, with a maximum of 350 words.)

## 1. Naming Standards for Version Control and Files - Use semantic versioning: - Major.Minor.Patch (e.g., v1.0.0, v1.1.0, v1.1.1) - Major version changes = breaking changes or major new features (e.g., adding eCommerce module). - Minor version changes = new features that do not break existing functionality (e.g., adding reporting filters). - Patch version changes = bug fixes or small improvements. - Branch naming conventions: - main (production‑ready code) - dev (integration branch) - feature/<feature-name> (e.g., feature/login-page) - bugfix/<issue-name> - File naming: - Use lowercase, hyphens, and descriptive names (e.g., shopping-cart.php, product-controller.php). - Avoid spaces or special characters. ## 2. Folder Structure / File Organisation Code /src /frontend /css /js /images /views /backend /controllers /models /services /database /tests /docs /config - /docs contains requirements, design documents, and technical notes. - /tests contains automated and manual test scripts. - /config stores environment configuration files (no passwords or sensitive data). - Structure supports scalability (required to handle 2,000 → 60,000+ transactions per week). ## 3. What Determines a Change of Version? - Major version: - New modules such as eCommerce, reporting, or customer access. - Architectural changes or database redesign. - Minor version: - Adding new UI pages, new search filters, new reporting fields. - Patch version: - Bug fixes, UI adjustments, security patches. - Version increments occur only after merging into dev or main. ## 4. Steps for Entering and Updating Files - Step 1: Create a feature branch - git checkout -b feature/<feature-name> - Step 2: Develop and test locally - Use developer workstation (business case risk: server delays). - Step 3: Stage and commit changes - git add . - git commit -m "Meaningful message: what changed and why" - Step 4: Push to GitHub - git push origin feature/<feature-name> - Step 5: Create Pull Request (PR) - Include description, screenshots, and link to requirement/user story. - Step 6: Code review by another developer - Ensures quality and governance compliance. - Step 7: Merge into dev - Only after approval and automated checks pass. - Step 8: Merge into main - After sprint completion and testing. - Step 9: Tag version - git tag v1.0.0 → git push --tags

Task 3: Create a collaborative environment for the team

In this task you need to set up the team collaboration environment using the collaboration software identified in Part 1 of this assessment.

You need to:

- add your assessor and 2 - 3 other students (as your team members in the scenario) performing key tasks on the project as contributors – the business case outlines the roles of the team members

- have some conversations and share documents amongst the team members and take screenshots of the interactions - include a screenshot of the activity in the space provided.

## Part 3: Monitor the use of the software management tools

Issues and challenges are a normal part of any project. Once you start working on the shopping portal project you will encounter multiple scenarios and will need to monitor and manage them in several ways using the software management tools identified earlier. This includes:

- assessing project progress in light of the issues, and updating the project plan to reflect any changes/delays that may happen as a result of the issues

- addressing the issues/changes in the source-control system used for the project

- communicating the changes/issues with the appropriate team members via the collaboration software used for the project.

Assume that the following situations occurred in the shopping portal project. Read through each scenario and address it using the appropriate software management tool.

Scenario 1: Project delays

According to your project plan, development of the shopping portal is due to start in one week. However, you just received a call from Alison Garmen, the IT Manager at Sports Warehouse, advising you that the project servers will not be available for another two weeks, which includes your development server. They also inform you about a possible integration with some banking software, which may add in 25 extra days to the development timelines. You will need to discuss the technicalities about the integration with two other key team members, but they called in sick.

You have decided you need to:

- locate a temporary environment to commence development – possibly the developers’ workstations

- factor in project delays due to the delays in receiving the servers

- factor in extra development time due to the banking integration

- factor in delays due to team members being sick – you estimate two days each.

Task 1: Act in response to scenario 1

To act in response to scenario 1 you need to update the project plan created in Part 2 of this assessment – you need to account for the delay in development due to the delays with equipment delivery as well as the delays that will happen due to team members being unwell.

Please also refer to the business case document (Long URL: https://share.tafensw.edu.au/share/items/9ca215f3-9cb3-4c9b-b8cf-c074d5645502/0/?attachment.uuid=0ddde1e7-4989-4a3a-8125-e383820606b6) as well as the Gelos ICT Governance policy to understand your responsibility around maintaining and reporting project progress. (Long URL: https://share.tafensw.edu.au/share/items/5f1cec7b-1d03-446a-85b7-edb42692c34e/0/?attachment.uuid=7041aeea-1a17-4f66-839d-f96f5c24d143)

Submit the updated project plan as evidence of completion of this task – highlight the updates made due to the delays just mentioned.

Scenario 2: Version control

Some basic webpages have been created for the shopping portal – click here to access them. (Long URL: https://share.tafensw.edu.au/share/items/9ca215f3-9cb3-4c9b-b8cf-c074d5645502/0/?attachment.uuid=54c982ba-9d35-4b24-8769-1ab0e570fc2b)

The student will need to upload the webpages to the source-control system identified in Part 1. The webpages include version 1 of the website with most of the webpages yet to be designed. However, the development team has added the login feature to the website.

Task 2: Act in response to scenario 2

According to the source-control procedures and guidelines established in Part 2, Task 2 document the following, as to how would you monitor the use of source-control system accurately:

- Assuming this is the first version of the website, what will be the name of this version of website?

- Enter some meaningful commit comments when pushing the files to the source-control system - write appropriate and meaningful commit comments before committing the code to the source-control system.

- Upload the website files to the source control system using the appropriate commands. Take screenshots of the steps involved in completing this task and include the screenshots in the space provided.

Scenario 3: Team collaboration

Team engagement and collaboration is crucial for a project to succeed. Therefore, as the project manager for the shopping portal project, you need to regularly use the collaboration software for team discussions, project updates and file sharing.

You usually start every working day with a quick check-in with your team members. On this occasion, use the check-in conversation to:

- discuss methods of using the source-control system to ensure the source code is correctly maintained

- discuss different ways that the collaboration environment can be used effectively in teamwork

- provide an update about the delays in the delivery of the IT equipment

- share the most up-to-date version of the project plan.

Don’t forget to refer to the Gelos Code of Conduct Policy and Procedure (Long URL: https://share.tafensw.edu.au/share/items/5f1cec7b-1d03-446a-85b7-edb42692c34e/0/?attachment.uuid=6b7e28d5-5226-450d-9ee8-b2567497512d) for understanding guidelines around appropriate team communication.

Task 3: Act in response to scenario 3

To act in response to scenario 3 you need to:

- monitor the collaboration environment and work with others to achieve joint outcomes

- ensure that all team members are included in the team chat

- facilitate effective group interaction and influence the direction of the conversation

- ensure all the points listed in scenario 2 are discussed

- take a leadership role in guiding and assisting your team.

Use the space provided to include screenshots of interactions/messages with your team.

## Checklist

The following checklist will be used by your Teacher/Assessor to mark your performance against the assessment criteria of your project. Use this checklist to understand what skills and/or knowledge you need to demonstrate during this assessment event. All the criteria described in the checklist must be met.

Table 2 — Assessment checklist

| Task number | Did the student do the following? | S | U/S | S | U/S | Assessor comments Record your comments in enough detail to demonstrate your judgement of the student’s performance against the criteria required. |
| --- | --- | --- | --- | --- | --- | --- |
| Part 1 Task 1 | Researches, checks project requirements and recommends an appropriate software development methodology – provides valid reasons for their choice. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 1 Task 2 | Researches, checks project requirements and recommends an appropriate project management software – provides valid reasons for their choice. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 1 Task 3 | Researches, checks project requirements and recommends an appropriate source-control system – provides valid reasons for their choice. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 1 Task 4 | Researches, checks project requirements as well as organisational policies and procedures to recommend an appropriate collaboration software – provides valid reasons for their choice. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 2 Task 1 | Student creates an initial project plan using the tool chosen in Part 1. The project plan should be documented according to the software specifications and project requirements. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 2 Task 1 | Student presents the project plan in a logical and easy to understand sequence. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 2 Task 2 | Student provides a list of source-control procedures that match up with the project and software specifications. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 2 Task 3 | Student sets up a collaboration environment using the tool recommended in Part 1 – this includes adding key team members outlined in the business case. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 3 Task 1 | Student monitors the project flow and adjusts the project plan accordingly. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 3 Task 2 | Student accesses and uploads the webpages to the source-control software in line with the source-control procedures. | ☐ | ☐ | ☐ | ☐ | Date: |
| Part 3 Task 3 | Student communicates the project delays to the team members via the collaboration software. The team members are also provided the updated project plan. | ☐ | ☐ | ☐ | ☐ | Date: |

## Assessment feedback

NOTE: This section must have the Teacher/Assessor and student signature to complete the feedback. If you are submitting through the TAFE NSW online learning platform, your Teacher/Assessor will give you feedback via the platform.

### Assessment outcome

☐ Satisfactory

☐ Unsatisfactory

### Assessor feedback

☐ 	Has the assessment declaration for this assessment event been signed and dated by the student?

☐ 	Are you assured that the evidence presented for assessment is the student’s own work?

☐ 	Was reasonable adjustment in place for this assessment event?

If yes, ensure it is detailed on the assessment document.

Comments:

### Assessor name, signature and date

### Student acknowledgement of assessment outcome

Would you like to make any comments about this assessment?

### Student name, signature and date

Michael Khalil
M.MAHER

20/3/2026