## Sheet1
Project: Sports Warehouse Online Retail Platform Project
Project Manager: Michael Khalil
Note:Updated for : Server delay (+2 weeks), sick leave (+4 days), banking integration (+25 days). All affected tasks highlighted.”
TASK | Start | End | Progress | Duration
Project Initiation and Setup | 2026-03-23 | 2026-04-05 |  | 13
Requirements Gathering | 2026-04-06 | 2026-04-26 |  | 20
Business Analysis and Backlog Creation | 2026-04-27 | 2026-05-10 |  | 13
System Design and User Interface Design | 2026-05-11 | 2026-05-31 |  | 20
Development Sprint 1 – Framework and Architecture | 2026-06-19 | 2026-07-02 |  | 13
Development Sprint 2 – Product Catalogue Module | 2026-07-03 | 2026-07-16 |  | 13
Development Sprint 3 – User Login and Authentication | 2026-07-17 | 2026-07-30 |  | 13
Development Sprint 4 – Prototype Build | 2026-07-31 | 2026-08-13 |  | 13
Banking Software Integration Development | 2026-08-14 | 2026-09-18 |  | 35
Development Sprint 5 – eCommerce and Shopping Cart | 2026-09-19 | 2026-10-02 |  | 13
Development Sprint 6 – Reporting and Analytics | 2026-10-03 | 2026-10-16 |  | 13
System Testing | 2026-10-17 | 2026-10-30 |  | 13
Performance and Load Testing | 2026-10-31 | 2026-11-13 |  | 13
User Acceptance Testing | 2026-11-14 | 2026-11-20 |  | 6
Deployment Preparation | 2026-11-21 | 2026-11-27 |  | 6
System Go‑Live | 2026-11-28 | 2026-12-04 |  | 6
Staff Training and Handover | 2026-12-05 | 2026-12-11 |  | 6
Post‑Implementation Review | 2026-12-12 | 2026-12-18 |  | 6
Formulas:
Duration = DAYS([End],[Start])